## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Data Analystics
INTERN NAME: | Shruti Ganesh Wagh
PROJECT NAME: | Student Performance Analysis
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2024-09-20

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Performanace Analysis |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
|  | Delay in obtaining specific datasets | Data Collection | Requests for data were not responded to within expected timelines. | Hold data access meetings to facilitate prompt data sharing. | Hold data access meetings to facilitate prompt data sharing. | Project Manager | Closed | Adjusted timeline to accommodate data delays.
|  | Visualization feedback took longer than expected | Visualization | Multiple rounds of feedback from stakeholders requested | Plan for iterative review cycles; set visualization standards early. | Schedule review sessions and feedback cycles in the timeline. | Visualization Lead | Closed | Established review cycles for next project
|  | Project objectives required reclarification | Project Planning | Some stakeholders requested clarification on goals post-initiation. | Ensure all stakeholders fully understand objectives; conduct a kickoff meeting. | Organize a detailed kickoff meeting for next project. | Project Manager | Closed | Clarified goals reduced ambiguity and improved focus.
|  | Unexpected data challenges affected analysis | Analysis | Inconsistencies in initial data quality review indicated potential delays. | Allocate buffer time for handling data issues during analysis. | Schedule contingency time for high-risk phases. | Project Manager | Open | Buffer time is now part of the schedule template.
|  | Delays in report finalization due to consolidation needs | Reporting | Multiple team members needed to contribute to final document. | Standardize report format early; assign specific sections to each team member. | Define roles for report compilation in future projects. | Documentation Lead | Closed | Streamlined process with early