## Intro
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Shruti Ganesh Wagh
Document Created On: | 2024-09-17
Version: | 1
s

## Project Plan
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Student Performance Analysis
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Power Bi Dashboard/Presentation
PROJECT SCOPE
PROJECT START DATE | 2024-08-15
PROJECT END DATE | 2024-09-15
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Objectives |  | 15-08-2024 | 2024-08-17 | 2 | COMPLETED
| 1.2 Project Planning |  | 15-08-2024 | 2024-08-17 | 2 | COMPLETED
| 1.3 Create a project charter |  | 15-08-2024 | 2024-08-17 | 2 | COMPLETED
| 1.4 Finalize project documentation |  | 15-08-2024 | 2024-08-17 | 2 | COMPLETED
2 Data Collection & Preparation
| 2.1 Data Cleaning & Transformation |  | 2024-08-17 | 2024-08-20 | 3 | COMPLETED
| 2.2 Verify data completeness and accuracy |  | 2024-08-17 | 2024-08-20 | 3 | COMPLETED
| 2.3 Standardize formats and validate data quality |  | 2024-08-17 | 2024-08-20 | 3 | COMPLETED
3 Data Analysis
| 3.1 Exploratory Data Analysis (EDA) |  | 2024-08-20 | 25-08-2024 2020 | 5 | COMPLETED
| 3.1.1 Generate descriptive statistics |  | 20-08-2024 | 25-08-2024 | 5 | COMPLETED
| 3.1.2 Visualize distributions of key metrics |  | 20-08-2024 2020 | 25-08-2024 | 5 | COMPLETED
| 3.2 Correlation Analysis |  | 25-08-2024 | 27-08-2024 | 3 | COMPLETED
| 3.1.2 Calculate correlations and document findings |  | 25-08-2024 | 27-08-2024 | 3 | COMPLETED
| 4: Visualization & Insights |  | 2024-08-28 | 31-08-2024 | 3 | COMPLETED
| 4.1 Data Visualization |  | 28-08-2024 | 31-08-2024 | 3 | COMPLETED
| 4.1.1 Design and create Power BI dashboard |  | 28-08-2024 | 31-08-2024 | 3 | COMPLETED
| 4.2 Insight Generation |  | 01-09-2024 | 10-09-2024 | 3 | COMPLETED
| 4.2.1 Interpret patterns, trends, and provide recommendations |  | 01-09-2024 | 10-09-2024 | 3 | COMPLETED
| 5: Reporting & Project Closure |  | 10-09-2024 | 14-09-2024 | 5 | COMPLETED
| 5.1 Presentation Preparation |  | 10-09-2024 | 14-09-2024 | 5 | COMPLETED
| 5.1.1 Prepare summary presentation for stakeholders |  | 10-09-2024 | 14-09-2024 | 5 | COMPLETED
| 5.2 Project Handover & Documentation |  | 10-09-2024 | 14-09-2024 | 5 | COMPLETED
| 5.2.1 Compile final report and documentation |  | 10-09-2024 | 14-09-2024 | 5 | COMPLETED
| 6 Closure |  | 15-09-2024 | 15-09-2024 | 1 | COMPLETED